## Changes
1 |  | Expected Completion Date | Remarks
Demand Collection Repeated Issue | 1 | 2023-01-09 | WIP
SMS & Mail Not Working | 2 |  | Mail Working / SMS service has to be renewed
A new user was created but Approval options are not listed like the rest of the users | 3 |  | Completed
Provision to Enter Staff PF Interest and to be displayed in the report. (Not needed in Daybook) | 4 | 2023-01-09 | Completed
Staff Festival Advance Balances are not correct | 5 | 2023-01-12 | Completed
Staff Personal Ledger Balances Fixed | 20 |  | Completed
All Vouchers should have approval | 6 | 2023-01-12 | WIP
Member Balance report currently only Opening Balance is begin generated, Till Date Balance with Date Filter required | 7 | 2023-01-16 | Yet to Start
FD Interest Amount both Provided and pending(Next Cycle) Date and Amount to be displayed | 8 | 2023-01-16 | Yet to Start
Balance Sheet - Every month Balance | 9 | 2023-01-23 | Yet to Start
Interest Certification - The interest Amount to be recovered should cover all the months instead of only march month | 10 | 2023-01-27 | Yet to Start
Demand Collected Balance (DCB) - Are not Matching with each head | 11 | 2023-01-27 | Yet to Start
Print Option for Rejected Loan | 12 | 2023-01-27 | Completed
Thrift and Dividend to be paid for all the years with selection Option | 13 | 2023-01-30 | Yet to Start
Bank Wise Investment Report | 14 | 2023-02-06 | Yet to Start
Cheque Print Option to be provided | 15 | 2023-02-06 | Yet to Start
In Approve Master Voucher Approval Option has to be added | 16 | 2023-02-06 | WIP
App - Pass word reset | 17 |  | Mobile App
FD-Metge (L.M.F(M.NO.10002) AND BEN FUND(M.NO.10010) to Emploees Union(M.NO.10011) | 18 | 2023-02-15 | Yet to Start
Mmbership - Closed member balance show as Zero. | 19 |  | Mobile App

## Issues Bugs
S.No | Date | Issue / Bug | Remarks | Status
1 | 2023-04-07 | March 2023 demand side total mistake is continue see the m.no 4497 Prerna Purohit surety loan pri. Show zero and should come Rs.10000/- then only the total is correct the same issue to m.no4148 . We posted March demand collection both member pri. Not affected correct and update . why it will come such mistake. | Value updated | Completed
2 | 2023-04-07 | Fixed deposit interest voucher not created. We have renewed fixed deposit on 5-4-2023 | Need to created a separate voucher only for interest through the application | To be updated by Thiruvirkonam
3 | 2023-04-12 | Fixed Deposit interest shows zero instead of actual value | Updated in the backed, need to find the root cause many instances updated in the backend last week | Temporary solution Provided
4 | 2023-04-15 | Retirement Employee Details not getting displayed | Currently we have removed the closed members from the list, Changed to code to display all the members. | Completed - Code shared need to updated in Production
5 | 2023-04-15 | Member no not getting displayed in the Demand Excel upload | PF no entered wronlgy informed to Gopu Sir | Completed
6 | 2023-04-15 | Share is not calculated correctly while raising the loan | Not a priority as this is one of case, working well for other scenarios | WIP